## Targeted Regression Plan
Release Item ID / Feature Name | Workstream | Impacted Workday BP(s) | Targeted E2E Job ID & Name | Selection Priority (High/Med/Low) | Risk & Impact Justification ("Why it must be tested") | Impact Type | Delivery Type | Release Number | Release Note URL
10864011 - Change Job New User Experience Initiation Improvements | HCM Core | Change Job | HCM_008 - Change Job to Pay | High | Mandatory redesign alters the initiation lifecycle, delays in-progress Change Job event creation until subprocess submission, and adds Move to New Manager warnings. This directly affects transactional state flow in HCM_008 - Change Job to Pay, risking unpropagated job attribute changes to downstream payroll. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcore/10864011.html
10981987 - Additional Payroll Data Enhancements | Payroll | Maintain Additional Payroll Data / Payroll Input | PAY_001 - Pay Input to Settlement | Med | Mandatory update introduces vendor-provided document attachments and collapsible field groups on the Additional Payroll Data task. Must be validated during pay input entry in PAY_001 - Pay Input to Settlement to prevent UI exceptions or missing third-party payroll deduction inputs. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/payexternal/10981987.html
9181338 - Mass Job Change | HCM Core | Mass Job Change / Change Job | HCM_008 - Change Job to Pay | Med | Introduces high-volume staffing updates using Mass Job Change on Mass Action Tables. Directly impacts the underlying Change Job business process and staffing data structures validated in HCM_008 - Change Job to Pay. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcore/9181338.html
10600329 - Language Support for Talent Highlights | Talent | Manage Career Profile / Talent Highlights | TAL_005 - Talent Elements (Succession Pool, Talent Pool and Career Profile) | Low | Extends multi-language support for AI-generated Talent Highlights content and source data displayed on Career Profiles. Directly impacts UI rendering and locale evaluation in TAL_005 - Talent Elements (Succession Pool, Talent Pool and Career Profile). | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/talins/10600329.html
10863799 - Override Change Job Field Access Using Security Groups | HCM Core | Change Job | HCM_008 - Change Job to Pay | High | Mandatory security enhancement allows configuring security groups for specific Change Job template fields, overriding step access. If field overrides block compensation or job classification fields, it breaks data propagation in HCM_008 - Change Job to Pay. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcore/10863799.html
10235672 - Advanced Lookup Table Snapshot Selection | Payroll | Maintain Lookup Table / Payroll Calculation | PAY_001 - Pay Input to Settlement | Med | Enhances View/Edit Lookup Table interface with snapshot prompts. Advanced lookup tables calculate wage bases and deduction rates during gross-to-net payroll execution in PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdarch/10235672.html
8693354 - Enhanced Change Job Experience Conversion | HCM Core | Change Job | HCM_008 - Change Job to Pay | High | Mandatory tenant-wide conversion retiring legacy Change Job experience and forcing Enhanced Change Job Experience across all templates and in-progress events. Directly alters initiation and approval workflows in HCM_008 - Change Job to Pay. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcore/8693354.html
11350396 - Manage Wellness Partner Connections and Use Cases | Benefits | Manage Wellness Partner Connections | No existing E2E Job found - Gap Identified | Low | Enables managing connection status and use cases of external wellness partners. This is a partner-hub integration administration task not covered by BEN_001 or any existing catalog job. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrbenx/11350396.html
10599981 - Attachments for Payroll Processing Checklists | Payroll | Process Payroll / Payroll Processing Checklist | PAY_001 - Pay Input to Settlement | Med | Enables uploading and viewing attachments on payroll processing checklist items in Payroll Hub. Directly alters operational settlement checklist steps in PAY_001 - Pay Input to Settlement. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdcore/10599981.html
10674984 - Feature Opt-In Removed for Restrict Job Profile Visibility by Country and Organization on Job Requisition Tasks | HCM Core | Create Job Requisition / Edit Job Requisition | REC_001 - Create to Close (Job Requisition) | High | Mandatory removal of feature opt-in permanently enforces job profile visibility restrictions by country, company, and organization during job requisition creation. Directly impacts job profile prompt filtering in REC_001 - Create to Close (Job Requisition). | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcore/10674984.html
11362334 - Worker Data - Leave Management | Benefits | Request Leave of Absence / Connected Absence API | ABS_001 - Leave Processing (Paid and Unpaid) | Med | Delivers leave management configuration and Get Workers Data API overrides for Connected Absence partners. Modifies absence plan and worked hours data structures shared with ABS_001 - Leave Processing (Paid and Unpaid). | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrbenx/11362334.html
11184353 - California State Disability Deductions | Payroll | Calculate Payroll / Maintain Tax Rules | PAY_001 - Pay Input to Settlement | High | Mandatory statutory update for California State Disability Insurance (SDI) taxable wages when wages are allocated across multiple states. Incorrect wage resolution causes severe payroll tax compliance failures during PAY_001 - Pay Input to Settlement. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdusa/11184353.html
9409258 - Document Security for Hiring Integrations | Integrations | Hire / Inbound Recruiting Integration | HCM_004 - Hire to Pay | Med | Delivers 3 new unconfigured security domains controlling document access for Kenexa and Unistaff hiring integrations. Alters document generation and attachment visibility during the Hire business process in HCM_004 - Hire to Pay. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcore/9409258.html
8397515 - Change Personal Information New User Experience | HCM Core | Change Personal Information | HCM_001 - Personal Elements Change (HR) | Med | Introduces redesigned user experience for standalone and onboarding personal information BPs with guided workflow, active consent, and Quick Tips. Directly alters UI steps in HCM_001 - Personal Elements Change (HR) and HCM_002 - Personal Elements Change (ESS). | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrpersoninf/8397515.html
11307375 - Canadian Tax Form Access via Self-Service Agent (SSA) | Payroll | Canadian Year-End Tax Query / SSA | No existing E2E Job found - Gap Identified | High | Adds conversational AI querying for Canadian year-end tax forms (T4, T4A, RL-1, NR4) via Self-Service Agent. Existing tax catalog job PAY_005 only covers US Federal/State/Local tax elections; no Canadian tax E2E job exists. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdcan/11307375.html
9786231 - Proration Based on Work Schedule Calendar | UK Payroll (Gap) | Calculate UK Payroll / Work Schedule Proration | No existing E2E Job found - Gap Identified | High | Mandatory UK payroll calculation update using work schedule calendars for mid-period proration. No UK Payroll regression jobs exist in E2E_Job_Catalog.xlsx (master catalog only has US Payroll PAY_001-PAY_005) - High-Risk Regulatory Gap! | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/wdmp/9786231.html
11365623 - Cancel Pay Complete Performance Update | Payroll | Cancel Pay Complete / Payroll Settlement | PAY_001 - Pay Input to Settlement | High | Mandatory architectural update improving Cancel Pay Complete performance and locking mechanisms. Directly impacts payroll completion rollbacks and reprocessing steps executed in PAY_001 - Pay Input to Settlement. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdarch/11365623.html
8959816 - Corrective Accounting for Retroactive Pay and Reallocation Status Management | Payroll | Pay Accounting Reallocation / Retroactive Pay | PAY_001 - Pay Input to Settlement | High | Mandatory update ensuring retroactive pay adjustments generate corrective accounting reallocations to match updated worktags. Directly impacts ledger postings and retro settlement in PAY_001 - Pay Input to Settlement and COMP_002 - Compensation Change to Pay (Retro). | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdacct/8959816.html
11197829 - Data Changes on Demand REST API | Payroll | Data Changes on Demand / Payroll Integration | PAY_001 - Pay Input to Settlement | Med | Delivers new REST API for Data Changes on Demand to extract delta worker payroll changes without full sweeps. Affects upstream data extraction feeding pay calculations in PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/payexternal/11197829.html
7690996 - Dependent Effective Dating | Benefits | Manage Dependents / Change Benefits | BEN_001 - Change Benefits | High | Mandatory feature introducing effective dating for worker dependents, tracking changes over time and preventing gaps in coverage histories. Directly alters dependent eligibility validation in BEN_001 - Change Benefits. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hrbendep/7690996.html
10609406 - Earned Wage Access | Payroll | Earned Wage Access / Payroll Deductions | PAY_001 - Pay Input to Settlement | Med | Enables Earned Wage Access (EWA) deduction integration with third-party providers. Modifies payroll deduction calculation rules executed in PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdpymt/10609406.html
10609408 - Enhanced Direct Deposit | Payroll | Maintain Payment Elections | PAY_004 - Payment Elections (Regular and Bonus) | High | Mandatory enhancement to Direct Deposit setup and validations. Modifies worker account verification and disbursement routing rules in PAY_004 - Payment Elections (Regular and Bonus). | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdpymt/10609408.html
10582777 - Exclude Workers from Retro Pay Calculation | Payroll | Run Retroactive Pay / Exclude Workers | COMP_002 - Compensation Change to Pay (Retro) | High | Mandatory capability to exclude specific workers from Retro Pay Calculation. Directly impacts retro calculation batches and worker selection logic in COMP_002 - Compensation Change to Pay (Retro) and ABS_003 - Retro Leave to Pay. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdretro/10582777.html
10452926 - Integration Recoverability for Global Payroll Connect | Payroll | Global Payroll Connect / PECI Integration | No existing E2E Job found - Gap Identified | Med | Enables restarting failed PECI/WECI integrations using completed DIS documents. Catalog lacks dedicated Global Payroll Connect / PECI integration E2E jobs - Integration Gap Identified. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/payexternal/10452926.html
10681278 - U.S. Federal - Personnel Action Request Payroll Status Indicator | HCM Core | Personnel Action Request (PAR) / Payroll Status | No existing E2E Job found - Gap Identified | Med | Mandatory U.S. Federal government enhancement adding statuses to Personnel Action Status field and enabling PAR resending. Catalog lacks dedicated U.S. Federal PAR E2E test cases - U.S. Federal Gap Identified. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hreg/10681278.html
11153925 - U.S. Federal: Enhancements to Nature of Action Setup | HCM Core | Personnel Action Request Setup / Nature of Action | No existing E2E Job found - Gap Identified | Low | Mandatory U.S. Federal report update separating Legal Authorities and Remarks columns in Nature of Action setup. Administrative/setup reporting feature with no matching job in catalog. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hreg/11153925.html
11405110 - Last Updated By Worker or System Account | Payroll | Maintain Worker Tax Elections | PAY_005 - Tax Elections - Federal, State and Local | High | Mandatory reporting field indicating worker or system account that last modified U.S. tax elections on Worker Tax Election business object. Directly impacts audit trail validations in PAY_005 - Tax Elections - Federal, State and Local. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdusa/11405110.html
11103600 - Limit to Job Warning for Circular Calculations | Payroll | Calculate Payroll / Circular Reference Detection | PAY_001 - Pay Input to Settlement | Med | Delivers Limit to Job Warning for Circular Calculations checkbox to bypass blocking errors during payroll calculation. Directly impacts calculation engine error-handling in PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdcore/11103600.html
9908828 - Compensation Step Adjustment Mass Operation Management | Compensation | Compensation Step Adjustment / Mass Operation | COMP_001 - Compensation Change to Pay | Med | Introduces new Mass Operation Management task type for Compensation Step Adjustment to update grade step defaults at scale. Directly modifies compensation step assignments tested in COMP_001 - Compensation Change to Pay. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcomp/9908828.html
10600327 - Prompt Updates for AI-Generated Development Items | Talent | Manage Development Plan / AI Generation | TAL_004 - Development Plan | Med | Mandatory UI change standardizing the Generate with AI prompt for development items in Career Hub and Manager Insights Hub. Directly alters user interaction flow in TAL_004 - Development Plan. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/taladv/10600327.html
11254434 - Configure Case Closure Timelines | People Experience (Help) | Case Management / Edit Tenant Setup - Help | No existing E2E Job found - Gap Identified | Low | Enables configuration of auto-close timelines for HR cases in Workday Help. Help/Case Management is not covered in the master E2E job catalog. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/help/11254434.html
9971768 - UK RTI FPS Exceptions | UK Payroll (Gap) | UK RTI Full Payment Submission (FPS) Reporting | No existing E2E Job found - Gap Identified | High | Mandatory UK Payroll regulatory update adding negative Statutory Neonatal Care Pay (SNCP) exception reporting to UK RTI FPS reports. No UK Payroll compliance jobs exist in catalog - High-Risk Regulatory Gap! | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdgbr/9971768.html
11091830 - Minimum Wage Analysis Skill for the Payroll Agent | Payroll | Minimum Wage Analysis / Payroll Agent | No existing E2E Job found - Gap Identified | Low | Delivers local authority support for Minimum Wage Analysis Skill in conversational Payroll Agent. AI agent skills have no test coverage in catalog. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdusa/11091830.html
11148025 - No Pay Accounting Reallocation Prior To Date | Payroll | Maintain Payroll Accounting Options | PAY_001 - Pay Input to Settlement | Med | Introduces No Pay Accounting Reallocation Prior To Date to prevent reallocations prior to closed fiscal periods. Impacts accounting entries generated during payroll settlement in PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdacct/11148025.html
9816542 - On-Demand Payroll Result Recalculation | Payroll | Process On-Demand Payment / Recalculation | PAY_002 - Process On Demand Payment | High | Mandatory architectural update preventing on-demand payroll result recalculation conflicts when results are locked by background jobs. Directly alters execution reliability in PAY_002 - Process On Demand Payment. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdarch/9816542.html
11154151 - Percent-Based Bonus Plan Enhancements | Compensation | Request Compensation Change / Bonus Plan | COMP_001 - Compensation Change to Pay | High | Mandatory enhancement to percent-based bonus plans enabling multiple bonus plans with individual targets and prorated payout calculations. Directly impacts compensation calculation and downstream pay in COMP_001 - Compensation Change to Pay. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcomp/11154151.html
10364686 - U.S. Federal: Mass Cancel and Mass Correct for Personnel Action Requests | HCM Core | Personnel Action Request Mass Cancel / Correct | No existing E2E Job found - Gap Identified | Med | Delivers Mass Cancel and Mass Correct for U.S. Federal Personnel Action Requests. U.S. Federal PAR transactions lack coverage in master catalog. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hreg/10364686.html
11153965 - U.S. Federal: Post-Separation Personnel Action Request Data | HCM Core | Post-Separation Personnel Action Request | HCM_009 - Termination to Pay | Med | Mandatory U.S. Federal update ensuring post-separation PARs reflect accurate termination attributes. Modifies termination data structures downstream of HCM_009 - Termination to Pay. | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hreg/11153965.html
9783413 - Worker Addresses Purgeable Data Type | Cross Application | Purge Worker Data / Maintain Address Purge | HCM_003 - Change Contact Information | Low | Introduces Worker Addresses purgeable data type for data retention compliance. Alters contact data storage rules validated in HCM_003 - Change Contact Information. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrperson/9783413.html
8534258 - Pay Accounting Reallocation | Payroll | Pay Accounting Reallocation | PAY_001 - Pay Input to Settlement | Med | Enhances Pay Accounting Reallocation task to support reallocations by position and earning component. Impacts financial journal postings downstream of PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdacct/8534258.html
11319774 - Compensation Plan Rollout Process | Compensation | Roll Out Compensation Plans / Manage Compensation | COMP_001 - Compensation Change to Pay | High | Mandatory update to Compensation Plan Rollout Process replacing background tasks with optimized asynchronous framework. Affects compensation updates feeding COMP_001 - Compensation Change to Pay and ADVCOMP_001. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcomp/11319774.html
10635923 - U.S. Federal: Personnel Action Requests on Union Membership Event | HCM Core | Personnel Action Request on Union Membership | No existing E2E Job found - Gap Identified | Low | Enables initiating PARs upon union membership changes for U.S. Federal workers. Specialized federal union process not represented in catalog. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hreg/10635923.html
11092839 - Pay Accounting Reallocation by Status Report | Payroll | Pay Accounting Reallocation by Status Report | PAY_001 - Pay Input to Settlement | Low | Mandatory operational report detailing accounting reallocation status. Used for post-settlement audit during PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdacct/11092839.html
8534292 - Payroll Accounting Reallocation Fringe | Payroll | Payroll Accounting Reallocation Fringe | PAY_001 - Pay Input to Settlement | Med | Delivers fringe benefit cost reallocation during payroll accounting runs. Impacts ledger distributions in PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdacct/8534292.html
10243485 - Payroll Circular Reference Calculation Warning | Payroll | Calculate Payroll / Circular Reference Warning | PAY_001 - Pay Input to Settlement | Med | Mandatory warning notification when circular component calculations occur during pay calculation. Directly alters batch run diagnostics in PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdcore/10243485.html
7510213 - UK Pensioner Payroll | UK Payroll (Gap) | UK Pensioner Payroll / Process Payroll | No existing E2E Job found - Gap Identified | High | Delivers dedicated UK Pensioner Payroll functionality to process occupational pension payments under PAYE rules. No UK Payroll jobs exist in master catalog - Critical Regulatory Gap! | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdgbr/7510213.html
10698163 - Learning Courses Linking to Development Items | Learning | Manage Learning / Manage Development Plan | LRN_001 - Create and Edit a Course, Program, Lesson, and Topic | Med | Enables linking learning courses directly to worker development items. Directly modifies course assignment metadata in LRN_001 and cross-functional integration with TAL_004 - Development Plan. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/taladv/10698163.html
10592579 - Get Workers REST API | Integrations | Get Workers REST API / Staffing Integration | HCM_004 - Hire to Pay | High | Mandatory API update adding email filtering parameters and surfacing pre-hire IDs for pending hires in Get Workers API. Downstream integrations consuming new worker records in HCM_004 - Hire to Pay are impacted. | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcore/10592579.html
10598633 - HMRC Gateway Credential Store | UK Payroll (Gap) | Maintain HMRC Gateway Credentials / UK RTI | No existing E2E Job found - Gap Identified | High | Mandatory UK tax authority credential management task per Employer Reference for RTI filings. No UK Payroll integration tests in catalog - High-Risk Gap! | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paygbrtech/10598633.html
10682930 - Simultaneous Compensation Changes Using Mass Compensation Actions During In Progress Change Job Event | Compensation | Request Compensation Change / In-Progress Change Job | COMP_001 - Compensation Change to Pay | High | Enables mass compensation actions to process workers who have an in-progress Change Job event. Directly tests concurrency resolution between HCM_008 - Change Job to Pay and COMP_001 - Compensation Change to Pay. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcomp/10682930.html
10674335 - U.S. Federal: Personnel Action Request Sequence Alerts | HCM Core | Personnel Action Request Sequence Validation | No existing E2E Job found - Gap Identified | Med | Mandatory alert preventing multiple PAR events with identical effective dates and non-zero sequence numbers. U.S. Federal specific - Gap Identified. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hreg/10674335.html
10609295 - UK Salary Sacrifice for Payroll Third-Party Payments | UK Payroll (Gap) | UK Salary Sacrifice / Payroll Third-Party Payments | No existing E2E Job found - Gap Identified | High | Mandatory support for UK Salary Sacrifice earning components in Payroll Third-Party Payments. UK Payroll gap in master catalog. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdcore/10609295.html
11197819 - Payroll Effective Change Interface Integration | Payroll | Payroll Effective Change Interface (PECI) | PAY_001 - Pay Input to Settlement | Med | Delivers Worker Has Additional Jobs field attribute on Worker Status section in PECI integration templates. Downstream payroll extract feeds touched during PAY_001 settlement are impacted. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/payexternal/11197819.html
10157141 - Payroll Instance Value Calculations for Work Schedule Calendars by Position | Payroll | Calculate Payroll / Work Schedule IVC | PAY_001 - Pay Input to Settlement | Med | Delivers new position-based Instance Value Calculations (IVCs) for work schedule calendars. Impacts proration formulas evaluated during PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/wdmp/10157141.html
10807256 - Language Fluency on the Configure Optional Fields Task | Talent | Manage Languages / Configure Optional Fields | TAL_005 - Talent Elements (Succession Pool, Talent Pool and Career Profile) | Low | Adds Fluent checkbox to Configure Optional Fields for Manage Languages BP. Directly impacts profile qualification maintenance in TAL_005. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/talpro/10807256.html
11191697 - Skills to Develop on Development Items SOAP APIs | Talent | Manage Development Plan / Put Development Item API | TAL_004 - Development Plan | Med | Mandatory v47.0 SOAP API update adding Skills to Develop fields to Put/Get Development Items web services. Impacts automated payload exchanges in TAL_004 - Development Plan. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/taladv/11191697.html
10601774 - Simultaneous Compensation Changes Using Request Quality Step Increase and Request Compensation Change | Compensation | Request Quality Step Increase / Request Compensation Change | COMP_001 - Compensation Change to Pay | High | Enables simultaneous in-progress execution of Request Quality Step Increase (QSI) and Request Compensation Change for the same worker. Directly impacts compensation concurrency in COMP_001 - Compensation Change to Pay. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcomp/10601774.html
9788605 - Payroll Processing Conflict Restrictions | Payroll | Cancel Pay Complete / Process On-Demand Payment | PAY_002 - Process On Demand Payment | High | Mandatory locking restrictions preventing simultaneous actions on payroll results while Cancel Pay Complete or On Demand calculation runs. Directly affects PAY_002 - Process On Demand Payment and PAY_001. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdarch/9788605.html
10438308 - Payroll Register by Period Report Performance Updates | Payroll | Payroll Register by Period Report | PAY_001 - Pay Input to Settlement | Low | Mandatory performance optimization for Payroll Register by Period report without changing output schema. Post-payroll validation step in PAY_001. | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdcore/10438308.html
9742827 - Payroll Third-Party Payments: Salary Sacrifice Enhancements | Payroll | Maintain Deduction Recipients / Payroll Third-Party Payments | No existing E2E Job found - Gap Identified | High | Mandatory enhancement to Create/Edit Deduction Recipient for UK salary sacrifice arrangements. UK third-party payment flow is not covered in catalog. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdacct/9742827.html
11012403 - Case Collaboration in Workday Help | People Experience (Help) | Case Collaboration in Workday Help | No existing E2E Job found - Gap Identified | Low | Enables multi-agent collaboration on Help cases. Case management is not covered in master catalog. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/help/11012403.html
11090319 - Article Downloading | People Experience (Help) | Article Downloading / Workday Help | No existing E2E Job found - Gap Identified | Low | Mandatory feature allowing users to download knowledge articles as PDFs in Workday Help. Not covered in master catalog. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/help/11090319.html
10680916 - Custom Calculated Health Care Rates | Benefits | Change Benefits / Health Care Rate Calculations | BEN_001 - Change Benefits | High | Delivers custom calculated rates for health care benefit plans based on worker attributes. Directly alters rate determination and deduction calculations in BEN_001 - Change Benefits and downstream payroll. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrbenenroll/10680916.html
9934542 - Periodic Tax Filing Integrations | Integrations | Periodic Tax Filing Integration / Payroll Tax | PAY_001 - Pay Input to Settlement | High | Mandatory integration updates for MasterTax, ADP, and Ceridian periodic tax filing integrations. Downstream tax filing extraction executed following PAY_001 - Pay Input to Settlement settlement is directly impacted. | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdi/9934542.html
9998285 - U.S. Federal - Personnel Action Request Business Process Consolidation | HCM Core | Personnel Action Request BP Consolidation | No existing E2E Job found - Gap Identified | Med | Consolidates multiple PAR business processes into a single unified BP definition for U.S. Federal. Catalog lacks federal PAR coverage. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hreg/9998285.html
8820298 - Report Trailing Payments to Prior Pay Groups with PECI | Payroll | Report Trailing Payments / PECI | PAY_001 - Pay Input to Settlement | Med | Enables PECI integration to extract trailing payments dispatched after worker pay group changes. Impacts pay history synchronization downstream of PAY_001. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/payexternal/8820298.html
10771045 - Request Edit Payroll Inputs Business Process | Payroll | Request Edit Payroll Inputs | PAY_001 - Pay Input to Settlement | High | Introduces new Request Edit Payroll Inputs business process enabling audited, workflow-driven edits to existing payroll inputs. Directly modifies pay input adjustment paths in PAY_001 - Pay Input to Settlement. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdinput/10771045.html
10322012 - Stock Vesting Schedule Enhancements | Compensation | Manage Stock Grants / Stock Vesting Schedule | COMP_001 - Compensation Change to Pay | Med | Enhances stock vesting schedule configurations and custom schedules. Modifies stock compensation awards tested in COMP_001 - Compensation Change to Pay and ADVCOMP_001. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcomp/10322012.html
11263559 - Run Retro Pay Calculation Performance Update | Payroll | Run Retroactive Pay Calculation | COMP_002 - Compensation Change to Pay (Retro) | High | Mandatory architectural update optimizing Run Retro Pay Calculation processing performance and memory management. Core engine impact directly affecting COMP_002 - Compensation Change to Pay (Retro) and ABS_003. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdretro/11263559.html
10998994 - Correct Change Job - Editable Fields Configuration | HCM Core | Correct Change Job | HCM_008 - Change Job to Pay | High | Delivers configurable field editing on completed Change Job events using Edit Correct Change Job Configuration. Directly modifies retroactive job correction steps in HCM_008 - Change Job to Pay. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcore/10998994.html
10636079 - U.S. Federal: Report Fields for Personnel Action Request Variables | HCM Core | Personnel Action Request Reporting Fields | No existing E2E Job found - Gap Identified | Low | Delivers new reporting fields for U.S. Federal PAR variables on Personnel Action business object. U.S. Federal reporting feature - Gap Identified. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hreg/10636079.html
10585617 - Standard Payroll Reports Performance Update | Payroll | Standard Payroll Reports / Payroll Settlement | PAY_001 - Pay Input to Settlement | Low | Mandatory performance updates to standard payroll audit reports used during payroll settlement signoff in PAY_001 - Pay Input to Settlement. | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdarch/10585617.html
11338977 - State Tax and Federal W-4 Withholding Access via Self-Service Agent (SSA) | Payroll | Withholding Tax Query / Self-Service Agent | PAY_005 - Tax Elections - Federal, State and Local | High | Enables worker self-service queries of State tax and Federal W-4 withholding selections via Self-Service Agent. Validates tax election data structures established in PAY_005 - Tax Elections - Federal, State and Local. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdusa/11338977.html
8826285 - State-Level Exceptions for Local Resident Taxes | Payroll | Maintain Tax Rules / State-Level Local Exceptions | PAY_005 - Tax Elections - Federal, State and Local | High | Mandatory statutory update for state-level exceptions on local resident taxes (e.g., PA Act 32 / MD counties). Miscalculated local taxes cause regulatory non-compliance in PAY_005 and PAY_001. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdusa/8826285.html
10292181 - Position Details on UK Payslip | UK Payroll (Gap) | Maintain Payroll Payslip Configuration / UK Payslip | No existing E2E Job found - Gap Identified | Med | Enables display of position details on UK payslips in UI and PDF format. UK payslip generation is not covered in catalog. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/wdmp/10292181.html
11126918 - Article Ownership | People Experience (Help) | Edit Tenant Setup - Help / Article Ownership | No existing E2E Job found - Gap Identified | Low | Mandatory tenant configuration enabling display of article ownership in Workday Help. Non-E2E HR Help feature. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/help/11126918.html
8521817 - Dependent Field Expansion: Garnishment-Relevant | Benefits | Maintain Dependents / Wage Garnishment Relevance | BEN_001 - Change Benefits | High | Introduces Garnishment-relevant flag on dependent records supporting wage garnishment calculations. Alters dependent data structures in BEN_001 and downstream payroll withholding in PAY_001. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrbendep/8521817.html
9235347 - Dependent Field Expansion: Relocation Data | Benefits | Maintain Dependents / Relocation Data | BEN_001 - Change Benefits | Low | Adds Dependent Relocation tracking for international assignments with effective dating. Extends dependent profile schema tested in BEN_001 - Change Benefits. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hrbendep/9235347.html
10721793 - Submit Payroll Input (Web Service) | Payroll | Submit Payroll Input Web Service | PAY_001 - Pay Input to Settlement | High | Mandatory optimization of Submit Payroll Input SOAP web service processing engine. Core inbound data pipeline directly executed during automated test runs of PAY_001 - Pay Input to Settlement. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdinput/10721793.html
10681276 - U.S. Federal - Mapping Options for PAR Agency Fields | HCM Core | Maintain Staffing Field Defaults / PAR Agency Fields | No existing E2E Job found - Gap Identified | Low | Delivers defaulting rules for agency-specific SF-50 fields on Personnel Action Requests. U.S. Federal specific setup - Gap Identified. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/hreg/10681276.html
10524525 - UK Court Orders From Different Issuing Authorities | UK Payroll (Gap) | Record UK Court Order for Worker | No existing E2E Job found - Gap Identified | High | Mandatory UK Payroll update allowing multiple court orders across different issuing authorities with protected earnings priority rules. No UK Payroll tests in catalog - High-Risk Gap! | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdgbr/10524525.html
10524527 - UK Court Orders From Different Issuing Authorities SOAP API Web Service | UK Payroll (Gap) | Put UK Court Order SOAP Web Service | No existing E2E Job found - Gap Identified | High | Delivers v47.0 web services to record UK court orders from multiple issuing authorities. UK Payroll web services not covered in catalog. | Direct Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdgbr/10524527.html
11307376 - US W-2 Box Value Queries via Self-Service Agent (SSA) | Payroll | W-2 Tax Document Queries / Self-Service Agent | PAY_005 - Tax Elections - Federal, State and Local | High | Enables worker conversational queries of W-2 box values via Self-Service Agent. Relies on tax election and year-end data validated in PAY_005 and PAY_001. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdusa/11307376.html
10635783 - W-2, W-2GU, and W-2VI Forms | Payroll | Generate W-2 / Year End Tax Forms | PAY_005 - Tax Elections - Federal, State and Local | High | Mandatory statutory update for 2026 tax year adding Box 12 Code 12 TA (Trump account contributions) and renaming Box 14a. Directly impacts year-end tax form generation downstream of PAY_005 and PAY_001 settlement. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdusa/10635783.html
10546221 - Job Profile Queries in Workday Graph API Schema | Workday Extend | Workday Graph API / Job Profile Query | REC_001 - Create to Close (Job Requisition) | Med | Mandatory Graph API schema enhancement exposing job classification, management level, and restrictions on jobProfile queries. Impacts external integrations and job profiles used in REC_001 - Create to Close (Job Requisition). | Downstream/Upstream Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/hrcore/10546221.html
10602095 - W-2C Forms | Payroll | Generate W-2C / Year End Tax Corrections | PAY_005 - Tax Elections - Federal, State and Local | High | Mandatory statutory update for W-2C corrected tax statements supporting H.R. 1 Box 12/14 changes. Affects tax correction processing downstream of PAY_005 and PAY_001 settlement. | Direct Impact | Mandatory | 2026R2 | https://doc.workday.com/release-notes/en-us/paywdusa/10602095.html
11197827 - Worker Effective Change Interface Integration | Payroll | Worker Effective Change Interface (WECI) | PAY_001 - Pay Input to Settlement | Med | Adds Worker Has Additional Jobs field attribute to Worker Status data section on WECI integration template. Touches downstream payroll interface payloads generated from worker changes in PAY_001. | Downstream/Upstream Impact | Optional | 2026R2 | https://doc.workday.com/release-notes/en-us/payexternal/11197827.html

## Executive Summary
WORKDAY RELEASE INTELLIGENCE & QE REGRESSION PLAN
Metric | Value | Context / Description
Total Release Items Analyzed | 87 | Total What's New items processed from release notes
Release Items with Direct / Downstream E2E Test Impact | 62 | Features mapped to existing regression suite
Identified Coverage Gaps (Missing E2E Tests) | 25 | Release features lacking test coverage in catalog
Master E2E Job Catalog Size | 42 | Total test inventory available in Master Repository
Targeted E2E Regression Jobs Selected | 17 | Unique tests scheduled for this release cycle
Regression Suite Reduction Percentage | 59.5% | Suite reduction (59.5%) within optimal bounds (20.0% - 85.0%).
High Priority Selected Items | 39 | Core business transactions and regulatory changes
Medium Priority Selected Items | 31 | Configuration-dependent UI and calculation updates
Low Priority Selected Items | 17 | Cosmetic or low-blast-radius opt-in items
SHA-256 Deliverable Integrity Checksum | 27602ba2857beff4343d37efbeab53c6... | Full SHA-256: 27602ba2857beff4343d37efbeab53c6a898747e21e80d1d37050aaf5afa1106